## ScoreCard
IT Project Scorecard Worksheet:
Project Title: |  |  | Project Number:
Project Leader/Manager: |  |  | Anticipated Project Start Date:
Sponsor: |  |  | Date Prepared:
This scorecard is a project management tool to be used in conjunction with Project Level Indicators and management experience as an aid in assessing a project's risk and complexity level. Once the project risk level is determined the Process, Methodology, and Documentation Guidelines will suggest the rigor and detail appropriate for that project risk level. This scorecard should be used as a guideline and not to render a decision on whether or not to move forward with a project. In addition, any project can be managed at a risk level higher than what it scores here, if desired.
Directions for use:
For each impact and difficulty listed select the appropriate level (in yellow) for this project from the drop down menus to arrive at a project total score.
Note: Weight factors (W*) shown are generally agreed upon defaults. Changes to the default values should be accompanied with written justification.
IT Project Scorecard Worksheet
Impact |  | W* | Difficulty |  | W*
Total Expenditures | Less than $50K (1pt) | 1 | Schedule Risk | Low (1pt) | 1
Effect on Business Goals | None or group (1pt) | 1 | Budget Risk | Low (1pt) | 1
Exposure | Low (1pt) | 1.5 | Quality/Performance Risk | Low (1pt) | 1
PII/FERPA | No (0 pts) | 1 | Complexity Risk | Low (1pt) | 1.5
|  |  | Innovation Risk | Low (1pt) | 1.5
Impact Total = | 3.5 |  | Difficulty Total = | 6
Project total = impact total x difficulty total = 21
Suggested score categories: Low Risk 21 - 200, Medium Risk >200 - 450, High Risk >450
W*: weight factor
Note: This scorecard is a "living document" with adjustments made based on experience and use.
Impact/Difficulty | Description
Total Expenditures | should include procurement costs, contractual costs, expected budget for new FTE's, and local staff labor costs
Effect on Business Goals | effect of the project's overall success or failure on the business goals of the unit, department or the university
Exposure | legal ramifications, e.g., HIPPA, G-L-B exposures, e.g., unsecured physical access, natural disasters, power outage
PII/FERPA | any electronic storage and transmission of Personally Identifying Information (PII) such as, Social Security number, Credit card number, Debit card number, Bank account number, Driver’s license number, or Passport number. handling of student data covered under the Family Educational Rights and Privacy Act (FERPA) which includes records, files, documents, and other materials that contain information directly related to a student.
Schedule Risk | degree of schedule compression, schedule uncertainty, amount of schedule dependence between this and other projects, harshness of penalty for schedule overrun
Budget Risk | degree of underfunding, degree of budget uncertainty, amount of budget spent on outside vendor or consulting agency product, harshness of penalty for budget overrun
Quality/Performance Risk | lack of margin of error in results, uncertainty in requirements, presence of externally mandated requirements, harshness of penalty for errors in performance
Complexity Risk | number of departments/units actively working on project, size of staff, project duration
Innovation Risk | amount of new technology, new processes and procedures, new management approaches

## Values
Total Expenditures | Effect on Business Goals | Data Exposure | PII/FERPA | Schedule Risk | Budget Risk | Quality Risk | Complexity Risk | Innovation Risk
Less than $50K (1pt) | None or group (1pt) | Low (1pt) | No (0 pts) | Low (1pt) | Low (1pt) | Low (1pt) | Low (1pt) | Low (1pt)
Between $50K and <$100K (2pts) | Departmental goals (3pts) | Low-Med (3pts) | Yes (30 pts) | Low-Med (2pts) | Low-Med (2pts) | Low-Med (2pts) | Low-Med (2pts) | Low-Med (2pts)
Between $100K and <$250K (3pts) | Goals across several (2-3) departments (5pts) | Medium (5pts) |  | Medium (3pts) | Medium (3pts) | Medium (3pts) | Medium (3pts) | Medium (3pts)
Between $250K and <$500K (4pts) | Goals across many (>3) departments (7pts) | Med-High (7pts) |  | Med-High (4pts) | Med-High (4pts) | Med-High (4pts) | Med-High (4pts) | Med-High (4pts)
Between $500K and <$600K (5pts) | University-wide goals (9pts) | High (9pts) |  | High (5pts) | High (5pts) | High (5pts) | High (5pts) | High (5pts)
Between $600K and <$750K (6pts)
Between $750K and <$900K (7pts)
Between $900K and <$1M (8pts)
$1M and over (9pts) *Major Project*